## M1_VotingSystem gantt charts
Tasks | Assigned To | Start Date | End Date | Health | Status | Notes
select project and start working on project
research on project and collect information | Siva Thathareddy | 2022-03-09 | 2022-03-11 | Green | Complete
make my project idea | Siva Thathareddy | 2022-03-12 | 2022-03-15 | Green | Complete
start working on implementation
work on implementation | Siva Thathareddy | 2022-03-16 | 2022-03-23 | Green | Complete
make mulitiple header file and complied | Siva Thathareddy | 2022-03-24 | 2022-03-26 | Green | Complete
make uml diagrams | Siva Thathareddy | 2022-03-27 | 2022-03-28 | Green | Complete
make doxygen file & documentation | Siva Thathareddy | 2022-03-29 | 2022-03-30 | Green | Complete
writing about project on git hub | Siva Thathareddy | 2022-03-31 | 2022-04-01 | Green | Complete

## Summary
At Risk | 0
Overdue Tasks | 6
Complete Count | 7
In Progress Count | 0
Not Started Count | 0